## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: |  |  | Progress Classes: | Ahead
Group Member: | Yonathan Kogan |  |  | On-track
Group Member: | Ivan Bulosan |  |  | Behind
Group Member: | Sheen Chua |  |  | Way Behind
Tutor: | Timothy Wiley
Class: | Friday 14:30-16:30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Yonathan Kogan | Ivan Bulosan | Sheen Chua
|  |  | Group Formed |  | Weekly Contribution | ms teams created | git repo created | did the menu with credits
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes | we decided to make the linked list as the bag
|  |  | Basic Main menu with "credits" |  |  | the array as the mossaic
|  |  | Choice of where to use linked list, vector & array |  |  | and the vector as the factories
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Yonathan Kogan | Ivan Bulosan | Sheen Chua
|  |  | Initial Design of ADTs (classes and potential methods) |  | Weekly Contribution | Linked List, player class, tile and node methods implemented | ADTS, player info, completed menu, user prompt, wrappers | Main menu
|  |  | Main menu |  | Issues
|  |  | User Prompt (for gameplay), but no/minimal error checking |  | Other Notes
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Yonathan Kogan | Ivan Bulosan | Sheen Chua
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | load, test cases. | Complete functionality to allow for single round gameplay
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Ahead
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Yonathan Kogan | Ivan Bulosan | Sheen Chua
|  |  | Fully complete implementation and error free |  | Weekly Contribution | test mode, edits on errors, scoring, endgame winner announcement | save game function, full error checking,
|  |  | Full error checking of user prompt |  | Issues |  | automated tile placement at end of round
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | On-track